## Risks
Sports Center Management System Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2018-03-15 | Compability in mobile application | Lack of compability depending on Android version | Technical Risk | 5 | 96% | 4.8 | User | We use 4.2 version of Android for preventing this risk.
2 | 2018-03-15 | Compability in mobile application | Lack of compability depending on Android version | Business Risk | 5 | 96% | 4.8 | Staff | We use 4.2 version of Android for preventing this risk.
3 | 2018-02-25 | Latency in development | Depending on only one team member in each development area | Schedule Risk | 5 | 80% | 4 | Staff | Each member in the team has some knowledge about all areas
4 | 2018-03-28 | Data loss about project | Loss of a project's supporting document | Resource Risk | 5 | 25% | 1.25 | Staff | All documents stored in project's GitHub repository.
5 | 2018-02-25 | Security issues on data process | While accessing to database, security problems that may occur | Technical Risk | 1 | 20% | 0.2 | User | While accessing to database, we use an indirect way.
6 | 2018-02-25 | Security issues on data process | While accessing to database, security problems that may occur | Business Risk | 4 | 99% | 3.96 | Staff | While accessing to database, we use an indirect way.
7 | 2018-03-03 | Security issues on data storage | Stored data injection risks | Business Risk | 5 | 93% | 4.65 | Staff | Passwords are encrypted first then stored in database.
8 | 2018-02-26 | Maintenance | Inflexible product | Business Risk | 3 | 99% | 2.97 | Stakeholders | We will implement a management panel for changes.
9 | 2018-02-25 | Unsatisfied customers | Not user-friendly product | Business Risk | 2 | 75% | 1.5 | Stakeholders | We will design interfaces as simple as possible.
10 | 2018-02-26 | Out-of-date technology | Not supported product for future uses | Technical Risk | 4 | 21% | 0.84 | Staff | We use recent technology for development.
11 | 2018-02-26 | Incomprehensible usage | User does not understand usage of the product | Business Risk | 2 | 50% | 1 | User | We will put a download link for user manual to each application.
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0
Note on E2: Risk Type = Direct or Indirect Resource Business Technical Schedule
Note on F2: Impact is a numerical value, usually between 1 and 5, that represents the impact to the project if the risk comes true. 5 is a HIGH IMPACT and 1 is LOW IMPACT.
Note on G2: Probability is the percentage chance that a risk will occur.
Note on H2: Magnitude is the result of the multiplication of Probability and Impact, providing a joint metric suitable for sorting.